## Phase-1
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-1: Analysis and Design | Requirement Gathering | Create Proposal | Anis |  |  | Anis
|  |  | Presenting proposal | Anis |  |  | Anis
|  |  | Analyse the feedback from presentation | Anis |  |  | Anis
|  |  | Create Specification | Anis
|  |  | Incorporate the additional requirements from feedback | Anis
|  | Analysing the requirements | Analysis the Specification | Team | Done | Done
Create Sample Layout
Present Sample layout and Get feedback from the client
Analyse the Feedback
|  | Finalizing the design layout | Create design and layout Incorporating the requirements | Suzon | 2017-06-12 | 2017-06-18 | 7
|  |  | Creation of Web Graphics, Page Backgrounds or website skins. | Suzon | 2017-06-19 | 2017-06-22 | 4
|  |  | Implementing Bootstrap framework | Suzon | 2017-06-27 | 2017-06-27 | 1
|  |  | Optimization of graphics to ensure a fast loading web page. | Masud | 2017-07-01 | 2017-07-01 | 1
|  | Testing and release | Test using the test cases e.g. compatibility, w3c standard | Anis | 2017-06-27 | 2017-06-28 | 1
|  |  | Submit the final design | suzon | 2017-07-02
|  | Feedback and Changes | Tweaks the changes and resubmit for approval | Suzon | 2017-07-03 | 2017-07-08 | 5
Formulas:
Duration = DATEDIF([Start date],[End date],"d")

## Phas-2
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-2: Website Front End Development | Database development | Analyse the requirements | Anis | 2017-07-12 | 2017-07-14 | 2
|  |  | Design the database schema | Forhad | 2017-07-15 | 2017-07-16 | 2
|  |  | Create the tables | rumi | 2017-07-16 | 2017-07-16 | 1
|  |  | Database Testing (using the test cases) | Sakib | 2017-07-16 | 2017-07-16 | 1
|  | Wireframe Development | Developing the wireframe | Suzon | 2017-07-02 | 2017-07-04 | 2
|  |  | Testing the wireframe |  | 2017-07-05 | 2017-07-06 | 1
|  |  | Release for the approval |  | 2017-07-08 | 2017-07-08 | 1
|  | Front end development | Database driven customisable Homepage | Sakib | 2017-07-16 | 2017-07-18 | 3
|  |  | Multi-level Dynamic Menu (Hamburger Menus) | Rumi | 2017-07-16 | 2017-07-18 | 3
|  |  | Database driven Page title and content with keyword settings | Sakib | 2017-07-20 | 2017-07-24 | 3
|  |  | Database driven Course information (as per HEFCE guidance) | forhad | 2017-07-20 | 2017-07-24 | 3
Course overview
Entry Requirements
Course Information
Course Cost
Module Information
Assessment/Feedback Information
|  |  | Faculty Information | Sakib | 2017-07-25 | 2017-07-27 | 3
|  |  | News and Notice Boards | Sakib | 2017-07-29 | 2017-07-31 | 2
|  |  | Contact Info and Contact Form | Rumi | 2017-08-01 | 2017-08-02 | 2
|  |  | Dynamic Header/Footer | Sakib | 2017-08-03 | 2017-08-05 | 2
|  |  | Photo Gallery and Videos | Rumi | 2017-08-03 | 2017-08-05 | 2
|  |  | Organisational Structure | Sakib | 2017-08-06 | 2017-08-08 | 2
|  |  | Community Engagement | Suzon | 2017-08-01 | 2017-08-03 | 2
|  |  | Alumni Page | Suzon | 2017-08-03 | 2017-08-05 | 2
|  |  | Feedback Form | rumi | 2017-08-06 | 2017-08-06 | 1
|  |  | Integrating with VLE | forhad | 2017-08-06 | 2017-08-08 | 3
|  |  | Integration with Important Links | Suzon | 2017-08-06 | 2017-08-06 | 1
|  |  | Captcha for spam prevention | Sakib | 2017-08-08 | 2017-08-10 | 2
|  |  | Sitemap and Site RSS Feeds | forhad | 2017-08-09 | 2017-08-10 | 2
|  |  | Accessibility for disabled people | forhad | 2017-08-12 | 2017-08-14 | 2
|  |  | Responsive (Support for mobile devices) | Suzon | 2017-08-07 | 2017-08-07 | 0
|  |  | SEO Friendly Coding | Anis | 2017-08-12 | 2017-08-12 | 1
|  | Testing | Usability Testing | masud | 2017-08-13 | 2017-08-13 | 1
|  |  | Functional Testing | masud | 2017-08-14 | 2017-08-14 | 1
|  |  | Compatibility Testing: | masud | 2017-08-15 | 2017-08-15 | 1
|  |  | Security Testing | rumi | 2017-08-17 | 2017-08-17 | 1
|  |  | Performance Testing | rumi | 2017-08-19 | 2017-08-19 | 1
|  | Bug fixing and release | Bug fixing | Sakib | 2017-08-19 | 2017-08-24 | 6
|  |  | Release for User Acceptance Testing | suzon | 2017-08-26 |  | 1
Formulas:
Duration = DATEDIF([Start date],[End date],"d")

## Phase-3
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-3: Content Management System (CMS) Development | Admin Panel development | Page Management - List/add/edit/delete | sakib | 2017-08-29 | 2017-09-07 | 9
|  |  | Menu Management -List/add/edit/delete | rumi | 2017-08-30 | 2017-09-09 | 9
|  |  | Course Management -List/add/edit/delete | sakib | 2017-09-09 | 2017-09-16 | 7
|  |  | Faculty management -List/add/edit/delete | rumi | 2017-09-10 | 2017-09-17 | 7
|  |  | Event/News Publishing-List/add/edit/delete | sakib | 2017-09-17 | 2017-09-21 | 5
|  |  | Photo Uploading -List/add/edit/delete | rumi | 2017-09-18 | 2017-09-23 | 5
|  |  | User Management-List/add/edit/delete | forhad | 2017-09-09 | 2017-09-16 | 7
|  | User Role and Access Control | Access Control | forhad | 2017-09-17 | 2017-09-19 | 3
|  |  | User Role -Admin/Editor/Guest | sakib | 2017-09-23 | 2017-09-24 | 2
|  |  | Page Creation with Rich Text Editor | rumi | 2017-09-24 | 2017-10-01 | 7
|  |  | User Login and forget password | sakib | 2017-09-25 | 2017-09-24 | 2
|  |  | User Profile | sakib | 2017-09-25 | 2017-10-01 | 4
|  |  | Edit profile and password | rumi | 2017-10-02 | 2017-10-03 | 2
|  | Testing | Usability Testing | Rumi | 2017-10-03 | 2017-10-04 | 1
|  |  | Functional Testing | Masud | 2017-10-04 | 2017-10-05 | 2
|  |  | Compatibility Testing: | Masud | 2017-10-07 | 2017-10-07 | 1
|  |  | Security Testing | Rumi | 2017-10-07 | 2017-10-07 | 1
|  |  | Performance Testing | Masud | 2017-10-07 | 2017-10-07 | 1
|  | Content Management | Creating pages | Suzon | 2017-10-03 | 2017-10-08 | 5
|  |  | Entering Course Information | Suzon | 2017-10-09 | 2017-10-12 | 4
|  |  | Entering Faculty information | Masud | 2017-10-03 | 2017-10-08 | 5
|  |  | Entering Event/News | Masud | 2017-10-09 | 2017-10-12 | 4
|  |  | Uploading Photos | Suzon | 2017-10-14 | 2017-10-16 | 3
|  |  | Creating users | Suzon | 2017-10-17 | 2017-10-19 | 3
|  | Testing and Bug Fixing |  | Sakib | 2017-10-02 | 2017-10-19 | 16
2017-10-21
Formulas:
Duration = DATEDIF([Start date],[End date],"d")

## Phase-4
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase - 4: Social Media Integration and Social marketing | Creating Account/Pages | Create Facebook page | Suzon | 2017-07-08 | 2017-07-08 | 1
|  |  | Create Twitter Page |  | 2017-07-08 | 2017-07-08 | 1
|  |  | Create LinkedIn Page |  | 2017-07-08 | 2017-07-08 | 1
|  |  | Creat Google+ page |  | 2017-07-09 | 2017-07-09 | 1
|  |  | Create Youtube Channel |  | 2017-07-09 | 2017-07-09 | 1
|  | Updating Contents | Upload content for Facebook page | Suzon+zim(DTP) | 2017-07-11 | 2017-07-18 | 7
|  |  | Upload content for Twitter Page |  | 2017-07-11 | 2017-07-18 | 7
|  |  | Upload content for LinkedIn Page |  | 2017-07-11 | 2017-07-18 | 7
|  |  | Upload content for Google+ page |  | 2017-07-11 | 2017-07-18 | 7
|  |  | Upload content for Youtube Channel |  | 2017-07-11 | 2017-07-18 | 7
|  | Integrating with Website | Integrating Facebook page | Forhad | 2017-07-26 | 2017-07-26 | 1
|  |  | Integrating Twitter Page |  | 2017-07-27 | 2017-07-27 | 1
|  |  | Integrating LinkedIn Page |  | 2017-07-28 | 2017-07-28 | 1
|  |  | Integrating Google+ page |  | 2017-07-30 | 2017-07-30 | 1
|  |  | Integrating Youtube Channel |  | 2017-07-31 | 2017-07-31 | 1
|  | Testing and Bug fixing | Testing Facebook page | Suzon | 2017-08-01 | 2017-08-01 | 1
|  |  | Testing Twitter Page |  | 2017-08-02 | 2017-08-02 | 1
|  |  | Testing LinkedIn Page |  | 2017-08-03 | 2017-08-03 | 1
|  |  | Testing Google+ page |  | 2017-08-05 | 2017-08-05 | 1
|  |  | Testing Youtube Channel |  | 2017-08-05 | 2017-08-05 | 1
Suzon + Zim(DTP) + Forhad
Formulas:
Duration = DATEDIF([Start date],[End date],"d")

## Phase-5
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-5: Registration & Enrolment Process Management | Creating Forms
Validating Entries
Uploading Files
Integrating with Website
Import/export to ICTM system
Testing and Bug fixi

## Phase-6
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-6: Student Portal & Forum | User functionalities
Messaging Boards
Forum
Full Site Testing

## Phase-7
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-7: Student Portal & Forum | User functionalities
Messaging Boards
Forum
Full Site Testing

## Phase-8
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-8: Searching content and Search Engine Optimization | Implementing searching
Search Engine Optimisation
Full Site Testing
Stat Analysis