## Phase-1
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-1: Analysis and Design | Requirement Gathering | Create Proposal | Anis |  |  | Anis
|  |  | Presenting proposal | Anis |  |  | Anis
|  |  | Analyse the feedback from presentation | Anis |  |  | Anis
|  |  | Create Specification | Anis
|  |  | Incorporate the additional requirements from feedback | Anis
|  | Analysing the requirements | Analysis the Specification | Team | Done | Done
Create Sample Layout
Present Sample layout and Get feedback from the client
Analyse the Feedback
|  | Finalizing the design layout | Create design and layout Incorporating the requirements | Suzon | 2017-06-12 | 2017-06-13 | 2
|  |  | Creation of Web Graphics, Page Backgrounds or website skins. |  | 2017-06-13 | 2017-06-14 | 2
|  |  | Optimization of graphics to ensure a fast loading web page. |  | 2017-06-15 | 2017-06-17 | 3
|  |  | Implementing Bootstrap framework |  | 2017-06-18 | 2017-06-19 | 2
|  | Testing and release | Test using the test cases e.g. compatibility, w3c standard | Masud | 2017-06-20 | 2017-06-22 | 3
|  |  | Submit the final design |  | 2017-06-23
|  | Feedback and Changes | Tweaks the changes and resubmit for approval | Suzon | 2017-07-01 | 2017-07-08 | 8
20

## Phas-2
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-2: Website Front End Development | Database development | Analyse the requirements | Forhad | 2017-07-09 | 2017-07-11 | 3
|  |  | Design the database schema |  | 2017-07-12 | 2017-07-13 | 2
|  |  | Create the tables |  | 2017-07-14 | 2017-07-16 | 3
|  |  | Database Testing (using the test cases) |  | 2017-07-16 | 2017-07-16 | 1
|  | Wireframe Development | Developing the wireframe | Suzon
|  |  | Testing the wireframe |  | 2017-07-01 | 2017-07-08 | 8
Release for the approval
|  | Front end development | Database driven customisable Homepage | Sakib | 2017-07-17 | 2017-07-19 | 3
|  |  | Multi-level Dynamic Menu (Hamburger Menus) |  | 2017-07-20 | 2017-07-22 | 3
|  |  | Database driven Page title and content with keyword settings |  | 2017-07-23 | 2017-07-25 | 3
|  |  | Database driven Course information (as per HEFCE guidance) |  | 2017-07-26 | 2017-07-30 | 4
Course overview
Entry Requirements
Course Information
Course Cost
Module Information
Assessment/Feedback Information
|  |  | Faculty Information |  | 2017-07-31 | 2017-08-03 | 4
|  |  | News and Notice Boards |  | 2017-08-04 | 2017-08-07 | 4
|  |  | Contact Info and Contact Form |  | 2017-08-08 | 2017-08-10 | 3
|  |  | Dynamic Header/Footer |  | 2017-08-11 | 2017-08-12 | 3
|  |  | Photo Gallery and Videos |  | 2017-08-13 | 2017-08-15 | 3
|  |  | Organisational Structure |  | 2017-08-15 | 2017-08-16 | 2
|  |  | Community Engagement |  | 2017-08-17 | 2017-08-17 | 1
|  |  | Alumni Page |  | 2017-08-18 | 2017-08-20 | 3
|  |  | Feedback Form |  | 2017-08-21 | 2017-08-22 | 2
|  |  | Integrating with VLE |  | 2017-08-22 | 2017-08-22 | 1
|  |  | Integration with Important Links |  | 2017-08-23 | 2017-08-23 | 1
|  |  | Captcha for spam prevention |  | 2017-08-23 | 2017-08-23 | 1
|  |  | Sitemap and Site RSS Feeds |  | 2017-08-10 | 2017-08-26
|  |  | Accessibility for disabled people |  | 2017-08-23 | 2017-08-23 | 1
|  |  | Responsive (Support for mobile devices) |  | 2017-08-24 | 2017-08-26 | 3
SEO Friendly Coding
|  | Testing | Usability Testing | Masud
Functional Testing
|  |  | Compatibility Testing: |  | 2017-08-27 | 2017-09-03 | 7
Security Testing
Performance Testing
|  | Bug fixing and release | Bug fixing | Sakib | 2017-09-04 | 2017-09-09 | 6
|  |  | Release for User Acceptance Testing |  | 2017-09-10
75

## Phase-3
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-3: Content Management System (CMS) Development | Admin Panel development | Page Management - List/add/edit/delete | Sakib | 2017-09-11 | 2017-09-13 | 3
|  |  | Menu Management -List/add/edit/delete |  | 2017-09-14 | 2017-09-16 | 3
|  |  | Course Management -List/add/edit/delete |  | 2017-09-17 | 2017-09-19 | 3
|  |  | Faculty management -List/add/edit/delete |  | 2017-09-20 | 2017-09-22 | 3
|  |  | Event/News Publishing-List/add/edit/delete |  | 2017-09-23 | 2017-09-25 | 3
|  |  | Photo Uploading -List/add/edit/delete |  | 2017-09-26 | 2017-09-28 | 3
|  |  | User Management-List/add/edit/delete |  | 2017-09-29 | 2017-10-01 | 3
|  | User Role and Access Control | Access Control |  | 2017-10-02 | 2017-10-03 | 2
|  |  | User Role -Admin/Editor/Guest |  | 2017-10-04 | 2017-10-05 | 2
|  |  | Page Creation with Rich Text Editor |  | 2017-10-06 | 2017-10-07 | 2
|  |  | User Login and forget password |  | 2017-10-08 | 2017-10-09 | 2
|  |  | User Profile |  | 2017-10-10 | 2017-10-10 | 1
|  |  | Edit profile and password |  | 2017-10-11 | 2017-10-11 | 1
|  | Testing | Usability Testing | masud | 2017-10-12 | 2017-10-13 | 2
|  |  | Functional Testing |  | 2017-10-14 | 2017-10-14 | 1
|  |  | Compatibility Testing: |  | 2017-10-15 | 2017-10-15 | 1
|  |  | Security Testing |  | 2017-10-16 | 2017-10-16 | 1
|  |  | Performance Testing |  | 2017-10-17 | 2017-10-18 | 2
|  | Content Management | Creating pages | Suzon | 2017-10-19 | 2017-10-21 | 3
Entering Course Information
Entering Faculty information
Entering Event/News
Uploading Photos
Creating users
|  | Testing and Bug Fixing |  | Sakib | 2017-10-21 | 2017-10-25 | 5

## Phase-4
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase - 4: Social Media Integration and Social marketing | Creating Account/Pages | Create Facebook page | Suzon
Create Twitter Page
Create LinkedIn Page
Creat Google+ page
Create Youtube Channel
|  | Updating Contents | Upload content for Facebook page
Upload content for Twitter Page
Upload content for LinkedIn Page
Upload content for Google+ page
|  |  | Upload content for Youtube Channel |  | 2017-07-08 | 2017-08-05 | 28
|  | Integrating with Website | Integrating Facebook page
Integrating Twitter Page
Integrating LinkedIn Page
Integrating Google+ page
Integrating Youtube Channel
|  | Testing and Bug fixing | Testing Facebook page
Testing Twitter Page
Testing LinkedIn Page
Testing Google+ page
Testing Youtube Channel

## Phase-5
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-5: Registration & Enrolment Process Management | Creating Forms
Validating Entries
Uploading Files
Integrating with Website
Import/export to ICTM system
Testing and Bug fixi

## Phase-6
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-6: Student Portal & Forum | User functionalities
Messaging Boards
Forum
Full Site Testing

## Phase-7
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-7: Student Portal & Forum | User functionalities
Messaging Boards
Forum
Full Site Testing

## Phase-8
Project | Phase | Milestone | Tasks | Assigned To | Start date | End date | Duration | Notes
www.iconcollege.ac.uk | Phase-8: Searching content and Search Engine Optimization | Implementing searching
Search Engine Optimisation
Full Site Testing
Stat Analysis